## Earned Value Management
AS AT 30 JUNE

Activity	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Jan	PV	% Complete	EV
Plan and staff project	4,000	4,000					8,000	100	8,000
Analyse requirements		6,000	6,000					12,000	100	12,000
Develop ERDs			4,000	4,000					8,000	100	8,000
Design database tables				6,000	4,000					10,000	100	10,000
Design forms, reports, and queries					8,000					8,000	100	8,000
Construct working prototype					10,000					10,000	12.34	1,234
Test/evaluate prototype					4,000	2,000					6,000		-
Incorporate user feedback					4,000	2,000					6,000		-
Test system					4,000	4,000	2,000			10,000		-
Document system					3,000	1,000		4,000		-
Train users					4,000		4,000		-
PV (Planned Value-Monthly)	4,000	10,000	10,000	10,000	12,000	10,000	4,000	6,000	6,000	4,000	5,000	5,000		86,000		47,234
EV (Earned Value-Monthly)	4,000	10,000	10,000	10,000	12,000	5,966
AC (Actual Cost - Monthly )	4,000	11,000	11,000	12,000	15,000	6,016

Historial data
Project PV (Cumulative)	4,000	14,000	24,000	34,000	46,000	56,000	60,000	66,000	72,000	76,000	81,000	86,000
Project EV (Cumulative)	4,000	13,000	21,500	30,500	41,500	51,966
Project AC (Cumulative)	4,000	15,000	26,000	38,000	53,000	59,016
CV=EV-AC	0	-2,000	-4,500	-7,500	-11,500	-7,050
SV=EV-PV	0	-1,000	-2,500	-3,500	-4,500	-4,034
CPI=EV/AC	1.000	0.867	0.827	0.803	0.783	0.881
SPI=EV/PV	1.000	0.929	0.896	0.897	0.902	0.928
Estimate at Completion (EAC)	97,667	$
Estimated time to complete	12.93	mths

					EAC

					EAC